## Sheet1
Task | WEEKS
TIMESPAN | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21
CORE FUNCTIONALITY | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN
Event Handler/Scheduler | bar: Week 16 MON to Week 16 WED
Database Parser | bar: Week 15 FRI to Week 15 SAT
Matrix Mapping | bar: Week 15 TUE
Breadth-First Search + Dijkstras | bar: Week 15 MON to Week 15 TUE
Account Manager | bar: Week 17 MON to Week 17 TUE
Ticket Suite | bar: Week 17 TUE to Week 17 WED
Journey Planner | bar: Week 16 WED to Week 16 FRI
Graphical User Interface | bar: Week 16 FRI to Week 17 MON
Database Implementation | bar: Week 15 WED to Week 15 FRI
Client Caching | bar: Week 15 SAT to Week 16 MON
Additional Functionality
Accessibility Features | bar: Week 17 FRI to Week 18 MON
Trip Advisor Integration | bar: Week 18 SUN to Week 19 MON
SMS Notifications | bar: Week 17 SUN to Week 18 TUE
Weather Predictive Delay Forecast | bar: Week 18 TUE to Week 18 FRI
Journey History/Quick Access | bar: Week 18 FRI to Week 18 SUN
Predictive Crowd Levels | bar: Week 19 MON to Week 19 FRI
Testing/Debugging
Penetration Testing | bar: Week 20 MON to Week 20 SUN
Stress Testing | bar: Week 19 FRI to Week 20 TUE
DEMO | bar: Week 17 THU; Week 19 THU
Error Correction/Debugging | bar: Week 20 SAT to Week 21 FRI
Deadline | bar: Week 21 FRI
Key
FLOAT TIME | bar: Week 15 MON